## Sheet2
Man Day for Each Resource | [5 empty] | Analyst Requirements | [7 empty] | Overhead - Gathering Requirements
No. | Resource | Wages/Month | Outcome/Month | Man Day | Total Days | No. | Resource | Man | Day | Effort | Man Day | Fixed Man Day | Fixed MD * Days | Man | Days | Plane | PP Client - Hotel | Hotel Room | Hotel | Allowance | Total
1 | Back-end Developer | 4500000 | 400000 | 245000 | 83 | 1 | Project Manager | 1 | 5 | 50% | 280000 | 350000 | 875000 | 2 | 3 | 930000 | 600000 | 1 | 1200000 | 1800000 | 4530000
3 | Front-end Developer | 4000000 | 400000 | 220000 | 33 | 2 | System Analyst | 1 | 5 | 50% | 260000 | 325000 | 812500
4 | Project Manager | 5200000 | 400000 | 280000 | 109 | [6 empty] | TOTAL | 1687500 | Overhead - Gathering UAT
5 | Quality Control | 2500000 | 400000 | 145000 | 12 | [8 empty] | Man | Days | Plane | PP Client - Hotel | Hotel Room | Hotel | Allowance | Total
6 | System Analyst | 4800000 | 400000 | 260000 | 10 | Development | [7 empty] | 3 | 3 | 1395000 | 600000 | 2 | 2400000 | 2700000 | 7095000
Total Costs | [5 empty] | No. | Resource | Man | Day | Effort | Man Day | Fixed Man Day | Fixed MD * Days
No. | Cost | Total Cost |  |  |  | 1 | Project Manager | 1 | 89 | 80% | 280000 | 350000 | 24920000 | Overhead - User Training
1 | Software Implementation Cost | 81552500 |  |  |  | 2 | System Analyst | 1 | 5 | 100% | 260000 | 325000 | 1625000 | Man | Days | Plane | PP Client - Hotel | Hotel Room | Hotel | Allowance | Total
2 | Overhead Cost | 20085000 |  |  |  | 3 | Back-end Developer | 2 | 56 | 100% | 245000 | 306250 | 34300000 | 4 | 3 | 1860000 | 600000 | 2 | 2400000 | 3600000 | 8460000
3 | Post Go Live Support (3 month) | 3675000 |  |  |  | 4 | Front-end Developer | 1 | 33 | 100% | 220000 | 275000 | 9075000
TOTAL |  | 105312500 | [9 empty] | TOTAL | 69920000
GRAND TOTAL |  | 115843750 | [11 empty] | Overhead Cost | [5 empty] | Total | 20085000
Debug and Testing
| Margin | 25% |  |  |  | No. | Resource | Man | Day | Effort | Man Day | Fixed Man Day | Fixed MD * Days
[6 empty] | 1 | Project Manager | 1 | 12 | 20% | 280000 | 350000 | 840000
[6 empty] | 2 | Quality Control | 1 | 12 | 100% | 145000 | 181250 | 2175000
[6 empty] | 3 | Back-end Developer | 2 | 12 | 20% | 245000 | 306250 | 1470000
[12 empty] | TOTAL | 4485000
Training and UAT
[6 empty] | No. | Resource | Man | Day | Effort | Man Day | Fixed Man Day | Fixed MD * Days
[6 empty] | 1 | Project Manager | 1 | 3 | 100% | 280000 | 350000 | 1050000
[6 empty] | 2 | Back-end Developer | 2 | 3 | 80% | 245000 | 306250 | 735000
[12 empty] | TOTAL | 1785000
Maintenance
[6 empty] | No. | Resource | Man | Day | Effort | Man Day | Fixed Man Day | Fixed MD * Days
[6 empty] | 1 | Back-end Developer | 1 | 12 | 100% | 245000 | 306250 | 3675000
[12 empty] | TOTAL | 3675000
[6 empty] | Software Implementation Cost | [5 empty] | Total | 81552500

## Sheet1
PM | 5 | 8 | 2 | 5 | 16 | 17 | 5 | 5 | 3 | 4 | 13 | 15 | 13 | 20 | 14 | 20 |  | 165 | 2 | 2 | 12 | 24 | 6 | 46
SA | 5 | [16 empty] | 5 | 2 |  |  |  |  | 2
FD |  | 8 | 2 | 5 | 16 | 17 | 5 | [10 empty] | 53 |  | 2 | 12 |  |  | 14
BE 1 | [7 empty] | 5 | 3 | 4 | 13 | 15 | 13 | 20 | 14 | 20 | 3 | 110 |  |  |  | 24 | 6 | 30
BE 2 | [7 empty] | 5 | 3 | 4 | 13 | 15 | 13 | 20 | 14 | 20 | 3 | 110 |  |  |  | 24 | 6 | 30
QC | [15 empty] | 20 |  | 20 |  |  |  |  | 6 | 6
| 5 | 6 | 2 | 3 | 11 | 8 | 3 | 56 | 12 | 4 |  | 89 |  |  |  |  | PM | 119
| 5 | [10 empty] | 0 |  |  |  |  | SA | 3
|  | 6 | 2 | 3 | 11 | 8 | 3 |  |  |  |  | 33 |  |  |  |  | FD | 39
[8 empty] | 56 | 12 | 4 |  | 56 |  |  |  |  | BE 1 | 80
[8 empty] | 56 | 12 | 4 |  | 56 |  |  |  |  | BE 2 | 80
[9 empty] | 12 | 4 |  | 0 |  |  |  |  | QC | 14