## Sheet1
| Man Day for Each Resource |  | Gathering Requirements | [5 empty] | Overhead - Gathering 1st Week
No. | Resource | Man Day | No. | Resource | Man | Day | Effort | Man Day | Man | Days | Plane | PP Client - Hotel | Hotel Room | Hotel | Allowance | Total
1 | Project Manager | 1000000 | 1 | Project Manager | 1 | 10 | 100% | 10000000 | 4 | 5 | 1860000 | 600000 | 1 | 2000000 | 6000000 | 10460000
2 | System Analyst | 900000 | 2 | System Analyst | 1 | 10 | 100% | 9000000
3 | Web Designer | 800000 | 3 | Web Designer | 1 | 10 | 100% | 8000000 | Overhead - Gathering 2nd Week
4 | Database Designer | 700000 | 4 | Web Developer 1 | 1 | 10 | 100% | 6000000 | Man | Days | Plane | PP Client - Hotel | Hotel Room | Hotel | Allowance | Total
5 | Web Developer | 600000 | 5 | Mobile Developer 1 | 1 | 10 | 100% | 6500000 | 4 | 5 | 1860000 | 600000 | 1 | 2000000 | 6000000 | 10460000
6 | Mobile Developer | 650000 | TOTAL |  |  |  |  | 39500000
7 | Quality Control | 800000 | Development | [5 empty] | Overhead - UAT
|  |  | No. | Resource | Man | Day | Effort | Man Day | Man | Days | Plane | PP Client - Hotel | Hotel Room | Hotel | Allowance | Total
Total Costs |  |  | 1 | Project Manager | 1 | 55 | 100% | 55000000 | 2 | 6 | 930000 | 600000 | 1 | 2400000 | 3600000 | 7530000
No. | Cost | Total Cost | 2 | System Analyst | 1 | 20 | 100% | 18000000
1 | Software Implementation Cost | 269450000 | 3 | Web Designer | 1 | 11 | 100% | 8800000 | Overhead - User Training
2 | Overhead Cost | 34980000 | 4 | Database Designer | 1 | 6 | 100% | 4200000 | Man | Days | Plane | PP Client - Hotel | Hotel Room | Hotel | Allowance | Total
3 | Post Go Live Support (1 month) |  | 5 | Web Developer 1 | 1 | 44 | 100% | 26400000 | 2 | 5 | 930000 | 600000 | 1 | 2000000 | 3000000 | 6530000
TOTAL |  | 304430000 | 6 | Web Developer 2 | 1 | 44 | 100% | 26400000
GRAND TOTAL |  | 334873000 | 7 | Mobile Developer 1 | 1 | 24 | 100% | 15600000 | Overhead Cost | [5 empty] | Total | 34980000
|  |  | 8 | Movile Developer 2 | 1 | 24 | 100% | 15600000
|  |  | 9 | Quality Control | 1 | 44 | 100% | 35200000
|  |  | TOTAL |  |  |  |  | 205200000
Deployment - UAT & Training
|  |  | No. | Resource | Man | Day | Effort | Man Day
|  |  | 1 | Project Manager | 1 | 11 | 100% | 11000000
|  |  | 2 | Web Developer 1 | 1 | 11 | 100% | 6600000
|  |  | 3 | Mobile Developer 1 | 1 | 11 | 100% | 7150000
|  |  | TOTAL |  |  |  |  | 24750000
|  |  | Software Implementation Cost |  |  |  | Total | 269450000